## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Prince Kumar Yadav |  | Login session not expiring after logout | Sprint 1 | Prince Kumar Yadav | Logical | Fixed session handling Logic | 2026-01-09 | Closed | Session security improved
2 | Prince Kumar Yadav | 2026-01-08 | Password stored in plain text initially | Sprint 1 | Prince Kumar Yadav | User Interface | Implemented password hasing | 2026-01-10 | Closed | Passwords secured
3 | Prince Kumar Yadav | 2026-01-12 | Product image not loading in production | Sprint 1 | Prince Kumar Yadav | User Interface | Corrected static folder path | 2026-01-13 | Closed | images working properly
4 | Prince Kumar Yadav | 2026-01-12 | Search bar not returing results | Sprint 1 | Prince Kumar Yadav | Logical | Fixed search route and query filter | 2026-01-14 | Closed | Search functioning correctly
5 | Prince Kumar Yadav | 2026-01-15 | Cart total calclation incorrect | Sprint 2 | Prince Kumar Yadav | Logical | Corrected total calculation logic | 2026-01-17 | Closed | Total verified
6 | Prince Kumar Yadav | 2026-01-18 | Duplicate item added to cart | Sprint 2 | Prince Kumar Yadav | Maintainability | Added duplicate check validation | 2026-01-20 | Closed | Cart clean and validated
7 | Prince Kumar Yadav | 2026-01-21 | Order created even payment failed | Sprint 2 | Prince Kumar Yadav | Standards | Added payments verification secured | 2026-01-23 | Closed | Payment validation secured
8 | Prince Kumar Yadav | 2026-01-25 | Payment signature mismatch error | Sprint 2 | Prince Kumar Yadav | Maintainability | Updated Razorpay signature verfication | 2026-01-28 | Closed | Gateway stable
9 | Prince Kumar Yadav | 2026-02-01 | Duplicate product suggestions | Sprint 3 | Prince Kumar Yadav | Logical | Applied Filtering logic | 2026-02-03 | Closed | Unique recommendation ensured
10 | Prince Kumar Yadav | 2026-02-05 | Incorrect recommendation for some users | Sprint 3 | Prince Kumar Yadav | Logical | Refined similarity calcuation | 2026-02-08 | Closed | Accuracy improved
11 | Prince Kumar Yadav | 2026-02-10 | Product URL not loading on laptop | Sprint 3 | Prince Kumar Yadav | Standards | Resolve DNS configuration issue | 2026-02-12 | Closed | Deployment stable
12 | Prince Kumar Yadav | 2026-02-14 | Database reset after restart | Sprint 3 | Prince Kumar Yadav | Standards | Configured persistent database | 2026-02-20 | Closed | Data persistence enabled

## Sheet2
Logical
User Interface
Maintainability
Standards
Others